## Sheet1
Task Name | Start Date | Number of Days
Sign-off Meeting | 2021-05-09 | 1
Deliver System | 2021-05-08 | 1
Test System | 2021-04-27 | 11
Build Business Logic | 2021-04-05 | 22
Link DB to Interface | 2021-03-24 | 11
Build Interface | 2021-03-12 | 12
Get Customer Approval | 2021-03-10 | 2
Build Class Diagram | 2021-03-01 | 9
Research User Interface Designs | 2021-02-27 | 9
Build Activity Diagrams for Each Use Case | 2021-02-15 | 23
Create Use Case Diagrams | 2021-02-11 | 8
Collect Requirements | 2021-01-22 | 14
44218